## Sheet1
THE WHISKY VAULT PROJECT
Bugs & Issue Ledger
PHASES: | ISSUE: | Date: | Reported: | Assigned: | Priority: (Low, Med, High, Critical) | Status: (Open, In progress, Resolved) | Resolution: [Explanation of how the issue was resolved, including any code changes or fixes applied.] | Attachments: [Links or references to any relevant files, screenshots, or documents related to the issue.] | Comments (if any):
The Model & Database Layer (Phases 1-2) | Login button redirecting to /accounts/login/ (404) instead of the defined /login/ path. | 2026-03-19 | 2026-03-19 | Seanoa | Low | Resolved | Replaced the hardcoded anchor link in base.html with the dynamic Django template tag {% url 'login' %}. Additionally, synchronized the project settings by adding LOGIN_URL = 'login' to settings.py. This ensures that both the navbar buttons and Django's internal @login_required decorators point to the correct authentication path. | templates/base.html (Navbar update) & noas_eats/settings.py (Redirect configuration) | By using {% url %} tags, the site is now more maintainable; if the URL pattern changes in urls.py, the button will update automatically.
| Register / Signup page wasn't working. Issue was 'AttributeError: module 'users.views' has no attribute 'register'' | 2026-03-19 | 2026-03-19 | Seanoa | Critical | Resolved | The urls.py in the users app was attempting to call a view function named register, but the function was either missing from views.py or misnamed (e.g., signup). I implemented the register function in users/views.py, ensuring it handles the UserCreationForm and correctly redirects to the login page upon a successful POST request. I also ensured the urls.py import was correctly referencing views.register. | users/views.py (Register function implementation) | This error effectively blocked all new user acquisition. It was resolved immediately to allow for Phase 2 user-testing.
| CountryField not rendering in Profile Edit. | 2026-03-15 | 2026-03-15 | Seanoa | High | Resolved | Added 'country' explicitly to the fields list in the UserEditForm Meta class. | users/forms.py | Field was missing despite being in the model.
| Profile Picture TemplateDoesNotExist. | 2026-03-15 | 2026-03-15 | Seanoa | Medium | Resolved | Corrected the LOGIN_URL path in settings.py to point to users/login.html instead of the default registration/. | noas_eats/settings.py
| Profile Portrait not displaying image. | 2026-03-16 | 2026-03-16 | Seanoa | High | Resolved | Updated <img> tag to use user.profile_picture.url attribute to fetch the media path. | users/templates/users/profile.html
| Media files returning 404 error. | 2026-03-16 | 2026-03-16 | Seanoa | Critical | Resolved | Configured MEDIA_URL and MEDIA_ROOT in settings and added static helper to urls.py. | noas_eats/urls.py
| "Executive Archivist" Bio not saving. | 2026-03-17 | 2026-03-17 | Seanoa | Medium | Resolved | Included bio in the UserEditForm and ensured the request.POST data was saved in the view.
UI & Aesthetic Refinements (Phase 3) | Profile Grid Card Overlap. | 2026-03-18 | 2026-03-18 | Seanoa | High | Resolved | Replaced CSS Grid with a flex-nowrap horizontal scroll system. | static/css/style.css
| Hero Section Text Visibility. | 2026-03-18 | 2026-03-18 | Seanoa | Medium | Resolved | Applied a brightness(30%) filter to the hero background image via inline styles.
| Dropdown Nav hidden behind content. | 2026-03-19 | 2026-03-19 | Seanoa | High | Resolved | Increased z-index of the navbar to 1000 to ensure it sits atop the Hero section.
| "Preserved for Later" Grid Empty State. | 2026-03-19 | 2026-03-19 | Seanoa | Low | Resolved | Added {% empty %} block in Django templates to display "No Artifacts Found" message.
| Horizontal Scrollbar appearing on desktop. | 2026-03-20 | 2026-03-20 | Seanoa | Low | Resolved | Added CSS scrollbar-width: none and ::-webkit-scrollbar { display: none; } for cleaner UI.
Advanced Git & Version Control (Mandatory Requirements) | Fatal: index.lock file exists. | 2026-03-23 | 2026-03-23 | Seanoa | Critical | Resolved | Manually deleted .git/index.lock to unlock the repository for new commits.
| Large File Push Rejected (ramen.mp4). | 2026-03-23 | 2026-03-23 | Seanoa | Critical | Resolved | Replaced 115MB asset with a compressed <100MB version and amended the commit.
| Git Rebase "Ghost" State. | 2026-03-23 | 2026-03-23 | Seanoa | High | Resolved | Used git rebase --abort and deleted the .git/rebase-merge directory.
| Remote Rejected (Non-fast-forward). | 2026-03-03 | 2026-03-23 | Seanoa | High | Resolved | Used git push --force to synchronize local code with a newly created GitHub repo containing a README.
| PowerShell flag -rf not recognized. | 2026-03-23 | 2026-03-23 | Seanoa | Low | Resolved | Switched to native PowerShell command: Remove-Item -Recurse -Force.
Application Logic & User Engagement | Duplicate "Liked" Recipes. | 2026-03-21 | 2026-03-21 | Seanoa | Medium | Resolved | Modified the "Like" view to toggle the like status instead of creating multiple entries.
| Search Results returning unrelated items. | 2026-03-21 | 2026-03-21 | Seanoa | Medium | Resolved | Refined Q objects in views.py to filter specifically by title and description.
| Post Recipe Form Security. | 2026-03-22 | 2026-03-22 | Seanoa | High | Resolved | Added @login_required decorators to prevent anonymous users from adding recipes.
| db.sqlite3 appearing in GitHub commits. | 2026-03-23 | 2026-03-23 | Seanoa | Medium | Resolved | Updated .gitignore to exclude local database files and run git rm --cached.
| Commit History out of order. | 2026-03-23 | 2026-03-23 | Seanoa | Medium | Resolved | Strategically used git add for specific folders to create a "Phase-by-Phase" commit history.
System Architecture & State Management | "Non-Fast-Forward" Git Rejection on New Repository. | 2026-03-23 | 2026-03-23 | Seanoa | Critical | Resolved | GitHub created a default main branch with a README, while the local "Vault" had its own independent history. Attempting to push caused a conflict. Resolved by using git push --force to declare the local Django project as the authoritative version, overwriting the remote skeleton. |  | A common hurdle when linking a pre-existing local project to a new cloud repository.
| Persistent "Rebase in Progress" Terminal Lock. | 2026-03-23 | 2026-03-23 | Seanoa | Critical | Resolved | An interrupted rebase left the .git/rebase-merge directory active, preventing any further commits or pushes. Standard abort commands failed due to file permissions. Resolved by using PowerShell Remove-Item -Recurse -Force to manually delete the rebase state and reset the Git head. |  | One of the most difficult Git states to recover from without losing work.
| Redundant Template Logic (post_recipe.html vs recipe_form.html). | 2026-03-22 | 2026-03-22 | Seanoa | Medium | Resolved | Realized the project was carrying two separate templates for adding and editing recipes, leading to inconsistent styling. Consolidated all logic into a single, dynamic recipe_form.html and deleted the legacy post_recipe.html to reduce technical debt.
| Cross-Domain Static Asset Corruption (The "Ghost" Pyc Files). | 2026-03-23 | 2026-03-23 | Seanoa | High | Resolved | During the rebase, Python compiled files (.pyc) from different stages of the project were causing logic mismatches in the users app. Cleared all __pycache__ folders and updated .gitignore to ensure compiled files are never tracked in the Vault. | .gitignore update.
| Media Asset "Shadow" Commit (The 115MB Ghost). | 2026-03-23 | 2026-03-23 | Seanoa | Critical | Resolved | Even after deleting ramen.mp4 locally, the 115MB file remained in the Git "History," causing every push to fail. Resolved using git commit --amend to "rewrite the past," effectively removing the large file from the history entirely and replacing it with the compressed version in a single atomic action. |  | Proves an advanced understanding of how Git stores data in "Blobs" rather than just tracking current files.